## Guru Construction Project Plan
Hierarchy | Task Name | Phase | Status | Phase Completed | Daily Log Link | Task Estimated Hours | Phase Estimated Hours | Phase Hourly Labor Rate | Phase Estimated Cost | Actual Hours | Actual Cost | Actual Cost Greater than Estimated | Start Date | End Date | Predecessors | Duration | % Complete
| Guru Construction — Office Renovation | [11 empty] | 2026-06-15 | 2027-03-04 |  | 189d | 0%
| Foundation | [11 empty] | 2026-06-15 | 2026-09-16 |  | 68d | 0%
| Site survey and assessment | Foundation | In Progress | [9 empty] | 2026-06-15 | 2026-06-15 |  | 1d | 0%
| Excavation and grading | Foundation | In Progress | [9 empty] | 2026-06-16 | 2026-08-12 | 3 | 42d | 0%
| Pour concrete footings | Foundation | In Progress | [9 empty] | 2026-08-13 | 2026-09-15 | 4 | 24d | 0%
| Inspect and sign off footings | Foundation | In Progress | [9 empty] | 2026-09-16 | 2026-09-16 | 5 | 1d | 0%
| Framing | [11 empty] | 2026-09-17 | 2026-11-30 |  | 53d | 0%
| Erect structural steel | Framing | In Progress | [9 empty] | 2026-09-17 | 2026-11-18 | 6 | 45d | 0%
| Install floor joists and subfloor | Framing | In Progress | [9 empty] | 2026-11-19 | 2026-11-20 | 8 | 2d | 0%
| Frame interior walls | Framing | In Progress | [9 empty] | 2026-11-23 | 2026-11-25 | 9 | 3d | 0%
| Install roof trusses | Framing | In Progress | [9 empty] | 2026-11-26 | 2026-11-27 | 10 | 2d | 0%
| Framing inspection | Framing | In Progress | [9 empty] | 2026-11-30 | 2026-11-30 | 11 | 1d | 0%
| Electrical | [11 empty] | 2026-12-01 | 2027-01-08 |  | 29d | 0%
| Rough-in wiring and conduit | Electrical | Not Started | [9 empty] | 2026-12-01 | 2026-12-03 | 12 | 3d | 0%
| Install electrical panel | Electrical | Not Started | [9 empty] | 2026-12-04 | 2026-12-04 | 14 | 1d | 0%
| Wire outlets and switches | Electrical | Not Started | [9 empty] | 2026-12-07 | 2026-12-07 | 15 | 1d | 0%
| Install lighting fixtures | Electrical | Not Started | [9 empty] | 2026-12-08 | 2027-01-07 | 16 | 23d | 0%
| Electrical inspection and sign off | Electrical | Not Started | [9 empty] | 2027-01-08 | 2027-01-08 | 17 | 1d | 0%
| Plumbing | [11 empty] | 2027-01-11 | 2027-02-17 |  | 28d | 0%
| Rough-in water supply lines | Plumbing | Not Started | [9 empty] | 2027-01-11 | 2027-01-13 | 18 | 3d | 0%
| Install drain and waste pipes | Plumbing | Not Started | [9 empty] | 2027-01-14 | 2027-01-15 | 20 | 2d | 0%
| Fit off fixtures and fittings | Plumbing | Not Started | [9 empty] | 2027-01-18 | 2027-02-16 | 21 | 22d | 0%
| Pressure test and inspect | Plumbing | Not Started | [9 empty] | 2027-02-17 | 2027-02-17 | 22 | 1d | 0%
| Finishing | [11 empty] | 2027-02-18 | 2027-03-04 |  | 11d | 0%
| Hang and finish drywall | Finishing | Not Started | [9 empty] | 2027-02-18 | 2027-02-18 | 23 | 1d | 0%
| Paint interior walls and trim | Finishing | Not Started | [9 empty] | 2027-02-19 | 2027-02-23 | 25 | 3d | 0%
| Install flooring | Finishing | Not Started | [9 empty] | 2027-02-24 | 2027-03-01 | 26 | 4d | 0%
| Fit cabinetry and joinery | Finishing | Not Started | [9 empty] | 2027-03-02 | 2027-03-03 | 27 | 2d | 0%
| Final clean and handover inspection | Finishing | Not Started | [9 empty] | 2027-03-04 | 2027-03-04 | 28 | 1d | 0%